FIRST MEETING ATTENDANCE, DIM3 + HOSPITAL “SPONSOR”

& COWORKERS

- PRE-MEETING – INFO FROM SALES BAXTER

  - Knowledge of PILOT ecosystems stakeholders. ESSENTIAL: IT info before meeting

  - Baxter to furnish hints and tips regarding the specific hospital and the relationships between stakeholders.

  - Knowledge of vision/needs in clinical Nutrition

  - Trigger a meeting with entry point sponsor & invited coworkers by sponsor.

- BEFORE MEETING

  - Do we send documents/video?

  - Do we make a Demo? To who? (attention language barrier)

  - Briefing with Baxter including Baxter interventions in meeting

- MEETING 1

  - Mutual introduction with roles: To be redacted.

  - Dim3 intro the solution, Scorso/Nutrow/Feedim – to be updated with Baxter for the specific contact.

  - Dim3 to illustrate the expected outcomes – to be updated with Baxter for the specific contact.

  - Hospital to describe its vision/needs in Clinical Nutrition needs. Better to know it before

  - Dim3 to illustrate a PILOT agreement framework.

  - Dim3 to illustrate the steps of a successful installations. In this part, it is worth to have former information on the IT systems and hierarchic structure (which Director has IT under his/her umbrella).

  - Dim3 to HIGH-LEVEL draft the data/tech needs and illustrate expected ‘burden’ on hospital resources.

  - Hospital to describe its organization including relationship with IT.

  - Hospital to describe the administrative pathway for a pilot project: pitfalls and critical step.

Expectations MEETING 1:

- OK to go further with next meeting and definition of major steps for the definition of pilot.

- Trigger a meeting with IT and Dim3 CTO

- Hospital to define a contact point.

- Parties to agree on a project governance, recurring meeting, etc etc

- DEBRIEFING AND EMISSION REPORT TO HOSPITAL SPONSOR

  - Agreed points.

  - Questions to be completed by both parts.

  - Action plan

- 2d MEETING

- Definition of a pilot project plan (what-happens-when)

- Financing questions from Hospital

- Definition of R&R dim3 and hospital side

- Proposal of a draft of pilot agreement

- Knowledge of legal/administration pathway in introducing project plan.