VETALYS

formerly DIATECH

MASTER ACTION PLAN & ORGANIZATIONAL STRUCTURE

Veterinary Allergy Diagnostics — European Launch 2026–2030

| Company | VETALYS (ex-DIATECH) |
| --- | --- |
| Document | Master Action Plan & HR Structure |
| Date | April 2026 |
| Authors | JCHYTECH |
| Status | Working Document — Confidential |

# PRELIMINARY NOTES & PROJECT CONTEXT

VETALYS (formerly DIATECH) is a France-incorporated veterinary diagnostics company. Its mission is to develop, import, and distribute allergy diagnostic solutions for companion animals (dogs and cats) across the European market. The company operates in a regulatory environment that is less burdensome than human IVD, providing a strategic window for rapid market entry.

Key Strategic Principles Exclusive focus on the veterinary sector — no mixing with human health products or catalog France is the validation and anchor market; EU expansion is upside, not a prerequisite Asset-light model: manufacturing outsourced to qualified Chinese partners (DIAHO / DIXUN) B2B distribution via established veterinary distributors (Centravet, Alcyon, Coveto) Instrumentation (reader/platform) is critical to long-term lock-in and data value Company name embeds 'Vet' branding — positioning as a proudly dedicated veterinary brand Technology transfer to European production is a medium-term strategic obligation Cross-shareholding structure between DIAHO (China) and VETALYS (Europe) — up to 40%

Name Change Note The name DIATECH is subject to trademark protection and must be replaced. The recommended naming direction is to include 'VET' in the brand identity (e.g., VETALYS) to signal exclusive veterinary focus, facilitate distributor recognition, and reinforce positioning vs. human diagnostic players.

PART I — MASTER ACTION PLAN

# 1. LEGAL & CORPORATE FOUNDATION

## 1.1 Company Incorporation & Structure

- Register VETALYS as a SARL (or SAS) under French law in Poitiers industrial area

- Define articles of association and governance rules — board composition, quorum, reserved decisions

- Establish beneficiary ownership register compliant with French transparency obligations

- Define shareholding structure: 60% founders (4 equal parts), 40% option reserved for DIAHO

- Register company with RCS, obtain SIRET/SIREN, VAT number, and EORI code for imports

- Open corporate bank account and configure financial accounting system (e.g., Sage, Pennylane)

## 1.2 Contractual Framework with Chinese Partners

- Sign Service Agreement with DIAHO: scope, deliverables, fees (€100,000 HT — 100% at signing)

- Execute Supply Framework Agreement: €50,000 ceiling, preferential pricing annex, exclusivity clause for Europe

- Formalize Exclusive European Distribution Agreement with DIAHO: territorial scope, exclusivity duration, minimum purchase commitments

- Execute Capital Option Pact (Pacte d'option): up to 40% entry, valuation mechanism, governance rights

- Sign Technology Transfer Agreement: timeline for kit and instrument production transfer to Europe

- Define IP ownership protocol: VETALYS retains all European regulatory dossiers and market rights

## 1.3 Legal Risk Mitigation

- Appoint French legal counsel specializing in cross-border commercial and IP law

- Ensure beneficiary transparency compliance — no proxy shareholding structures

- Register trademarks: VETALYS brand and associated logos in France + EU (EUIPO)

- Document and archive all contractual documents for 10-year regulatory retention requirement

# 2. REGULATORY & QUALITY COMPLIANCE

## 2.1 Regulatory Framework Assessment

Regulatory Baseline — Key Facts Veterinary IVDs are EXCLUDED from EU Regulation 2017/746 (IVDR) — no CE marking required Allergy kits (cat/dog) are non-regulated use — no ANSES NRL validation required French competent bodies: DGAL (Ministry of Agriculture) and ANSES Chemical compliance mandatory: CLP Regulation, REACH, French-language SDS Border veterinary control (SIVEP/CHED-A) applies ONLY if kits contain animal-derived materials Customs HS code: 3822.00 — diagnostic reagents ISO 9001 / ISO 13485 alignment is voluntary initially but strategically essential

## 2.2 Pre-Launch Regulatory Actions

- Confirm composition of all kit components — presence or absence of animal-derived materials (CHED-A trigger)

- Obtain full technical dossier from DIAHO/DIXUN: performance data (sensitivity, specificity, LOD), validated matrices, SDS

- Prepare French-language labels and IFUs (Instructions for Use) per CLP/REACH requirements

- Register UFI/PCN code for all reagent mixtures classified as hazardous marketed in EU

- Select and validate Border Control Post (PCF/SIVEP) entry point

- Prepare CHED-A documentation and TRACES-NT registration if animal-derived components confirmed

- Establish traceability and vigilance system: lot tracking, CAPA procedures, complaint/recall management

- Set up 10-year archiving system for technical documentation, COAs, performance data

## 2.3 Quality System Roadmap

- Phase 1 (2026): Implement operational quality documentation — SOPs, batch release, complaint handling

- Phase 2 (2027–2028): Align with ISO 9001 framework — quality manual, process mapping, internal audits

- Phase 3 (2028+): Pursue ISO 13485 certification to support CE-IVD technical file and institutional sales

- Appoint internal Quality Responsible (can be shared/part-time initially)

- Conduct annual supplier audits of DIAHO/DIXUN manufacturing site

## 2.4 Country-by-Country Regulatory Expansion

| Country | Language | EPR System | Border Control | Notable Req. |
| --- | --- | --- | --- | --- |
| France 🇫🇷 | French | National EPR | SIVEP/CHED-A | ANSES oversight |
| Germany 🇩🇪 | German | VerpackG/LUCID | BCP/CHED-A | FLI (notifiable) |
| Spain 🇪🇸 | Spanish | RD 1055/2022 | BCP/CHED-A | MAPA oversight |
| Italy 🇮🇹 | Italian | CONAI | BCP/CHED-A | Min. of Health |
| Belgium 🇧🇪 | FR + NL | Fost Plus/Valipac | BCP/CHED-A | FASFC/AFSCA |

# 3. PRODUCT PORTFOLIO & TECHNICAL READINESS

## 3.1 Core Product Portfolio

VETALYS launches with a strictly defined allergy diagnostics portfolio for companion animals. Product line extensions are contingent on commercial validation of the core offering.

| Product | Format | Target Price (€) | Use Case |
| --- | --- | --- | --- |
| Rapid Allergy Test | Lateral Flow (LFIA) | €35–39 (clinic net) | First-line, fast 10–15 min result |
| ELISA Allergy Kit | Plate-based ELISA | Per quote | Lab/referral clinics, batch testing |
| Dot Array Kit | Protein microarray | €120–150 | Complex/chronic cases, full allergen panel |
| DX Reader (instrument) | Digital reader + software | TBD | Standardised reading, data management, network |

## 3.2 Technical File Completion — CRITICAL PRIORITY

⚠ CRITICAL PRIORITY — Complete Technical Files required BEFORE any commercial or regulatory action. Required per product: performance data (sensitivity, specificity, LOD), stability studies, validated matrices, batch release criteria, manufacturing process, risk assessment, and SDS.

- Obtain and validate full technical dossiers from DIXUN for each SKU

- Translate performance summaries and IFUs into French (and target-market languages)

- Verify analytical validation data: sensitivity/specificity vs. reference method, cross-reactivity

- Confirm stability data: shelf life, temperature excursion tolerance, shipping conditions

- Obtain COA (Certificate of Analysis) templates and batch release protocols

- Review and qualify the DX Reader software for data management and network connectivity

- Maintain living technical file — update with each new batch and any performance variation

# 4. MARKET ENTRY — FRNCE (ANCHOR MARKET)

## 4.1 Market Landscape

| Market Size & Structure ~7,200 companion animal clinics 18,000 veterinarians 7.6M dogs + 15.1M cats Dermatology ≈ 20% of consultations 230k–290k tests/year addressable volume | Key Distributors Centravet — largest French vet distributor Alcyon — broad clinic coverage Coveto — specialist distribution Allergy prevalence: dogs 12–18%, cats 10–14% TAM France 2028 ≈ €12.6M |
| --- | --- |

## 4.2 Go-to-Market Phases

| Phase | Timing | Actions | KPIs |
| --- | --- | --- | --- |
| Phase 1 — KOL | Q1–Q2 2026 | Engage AFVAC dermatology opinion leaders; distribute evaluation kits; collect clinical feedback | 5–10 KOL clinics activated |
| Phase 2 — Distributors | Q2–Q3 2026 | Onboard Centravet/Alcyon/Coveto; training sessions; distributor activation kits; margin discussions | 2–3 distributor agreements signed |
| Phase 3 — Clinics | Q3–Q4 2026 | Direct-to-clinic activation through distributors; regional demos; webinar program | 100–200 clinics ordering |
| Phase 4 — Upsell | 2027 | Introduce DX Reader and Dot Array to repeat-ordering clinics; subscription/bundle offers | Reader placement rate, array attach rate |

## 4.3 Pricing Strategy

- Transfer price (DIXUN/DIAHO → VETALYS) as end market price: €35–39 (HTVA) rapid test

- Reader/instrument: separate equipment pricing model — consider lease/placement to accelerate adoption

- Distributor margin: explicitly modeled in P&L — net revenue = VETALYS invoicing price to distributor

- Introductory discount for first 3 orders per clinic — time-limited to accelerate trial

- Pricing avoids both extremes: not so low as to signal poor quality, not so high as to restrict routine use

# 5. EUROPEAN EXPANSION ROADMAP

## 5.1 Country Prioritization Matrix

| Country | Clinics | 2028 Pot. (M€) | CAGR | Complexity | Entry Year |
| --- | --- | --- | --- | --- | --- |
| France 🇫🇷 | 7,500 | €12.6M | 35% | Medium | 2026 |
| Italy 🇮🇹 | 8,000 | €13.0M | 33% | Medium | 2026–27 |
| Spain 🇪🇸 | 6,000 | €9.0M | 31% | Low | 2026–27 |
| Germany 🇩🇪 | 10,000 | €15.0M | 34% | High | 2027–28 |
| Belgium 🇧🇪 | 1,500 | €2.0M | 29% | Easy | 2026 opportunistic |

## 5.2 Expansion Sequencing

- 2026 — France launch + clinical validation + opportunistic Belgium (high distributor centralization, KOL network)

- 2026–2027 — Italy and Spain parallel expansion: multilingual labels, local distribution partnerships

- 2027 — Apply for CE-IVD technical file to support institutional and tender sales

- 2028 — Germany: full ISO 13485, German-language IFU, regulatory-grade technical file, premium positioning

- 2028 — European distribution hub operational; OEM integration in China manufacturing confirmed

# 6. OPERATIONS & SUPPLY CHAIN

## 6.1 Manufacturing Model

Manufacturing is fully outsourced to DIAHO in China. VETALYS retains control over product specifications, batch release criteria, and supplier oversight. Technology transfer to European production is a strategic medium-term objective.

- Formalize manufacturing requirements specification for each SKU with DIAHO

- Establish batch release protocol: QC tests VETALYS must run upon receipt before release to market

- Negotiate minimum order quantities (MOQ) and lead times compatible with French launch demand

- Plan initial stock holding: 3–6 months buffer at forecast volumes to avoid stockouts

- Configure cold chain logistics if needed: 2–8°C storage and transport where applicable

- Define inventory management system: lot tracking, FEFO (first expire, first out) management

- Initiate Technology Transfer Plan: timeline, milestones, and investment requirements for EU production

## 6.2 Import & Logistics Actions

- Register as EU Importer of Record — responsibilities for product compliance and documentation

- Select customs broker experienced in veterinary/diagnostic product imports

- Set up TRACES-NT account for CHED-A submissions if animal-derived components present

- Define and test import workflow: manufacturer → BCP/SIVEP → 3PL warehouse → distributor

- Implement ERP/inventory system or spreadsheet tracking for initial volumes

- Define reorder triggers and safety stock levels by SKU

# 7. FINANCIAL PLAN & MILESTONES

## 7.1 Five-Year P&L Summary (France Base Case)

| P&L Item (€) | Y1 | Y2 | Y3 | Y4 | Y5 |
| --- | --- | --- | --- | --- | --- |
| Total Revenue | €299,700 | €856,088 | €2,295,375 | €4,490,850 | €7,209,585 |
| Total COGS (50%) | €149,850 | €428,044 | €1,176,848 | €2,328,720 | €3,771,383 |
| Gross Profit | €149,850 | €428,044 | €1,118,528 | €2,162,130 | €3,438,203 |
| OpEx (excl. payroll) | €99,960 | €140,688 | €182,621 | €221,362 | €251,244 |
| Payroll | €0 | €91,000 | €237,200 | €420,970 | €700,780 |
| EBITDA | €49,890 | €196,356 | €698,706 | €1,519,798 | €2,486,179 |

Financial Notes Gross margin 50% maintained throughout — improvement via volume absorption Y1 payroll = €0: management compensated via service contract; external consultants for regulatory/commercial Interest and depreciation NOT included — to be modeled separately with investment strategy Subordinated loan of €100,000 from DIAHO provides initial runway; additional investor capital sought EU expansion (IT, ES, DE, BE) represents pure upside — France alone validates the investment case

## 7.2 Funding Priorities

- Tranche 1: Regulatory & import compliance setup (labels, SDS, TRACES, legal) — est. €15,000–25,000

- Tranche 2: Initial product stock & logistics (first import batch, 3PL setup) — est. €30,000–50,000

- Tranche 3: Commercial launch — distributor activation, KOL events, marketing materials — est. €20,000–30,000

- Working capital buffer: receivables from distributors (60–90 day terms typical) — est. €20,000–40,000

- Total estimated Y1 cash requirement: €100,000–150,000 (covered by DIAHO loan + founder contributions + subsidies or other investors)

# 8. RISK REGISTER & MITIGATION

| Risk | Severity | Mitigation | Owner |
| --- | --- | --- | --- |
| Supplier dependency | High | Contractual safeguards, dual-sourcing plan, tech transfer roadmap | COO / Supply Chain |
| Slower-than-expected adoption | Medium | Lean cost structure extends runway; no aggressive curve assumed | CFO / CCO |
| Regulatory delay (import, CHED-A) | Medium | Early preparation of technical files; customs broker engaged pre-launch | RA/QA Manager |
| Distributor dependency | Medium | Multi-distributor strategy; performance-based review; no single concentration | CCO |
| Technical file incompleteness | High | Critical priority — complete before any commercial action | RA/QA Manager |
| Trademark / name dispute | Low | EUIPO filing for VETALYS brand immediately after incorporation | Legal / CEO |
| Chinese partner governance risk | Medium | French law governs; transparent shareholding; legal counsel review all contracts | CEO / Legal |
| IVDR regulatory evolution | Low/Med | Monitor EU policy; ISO 13485 alignment provides proactive readiness | RA/QA Manager |

PART II — ORGANIZATIONAL STRUCTURE & HUMAN RESOURCES PLAN

# 9. DESIGN PRINCIPLES & ORGANIZATIONAL OVERVIEW

Design Principles Maximum output per euro of payroll — each hire must be justified by a revenue or compliance impact Year 1: founder/consultant model — minimize fixed payroll while maintaining execution capacity Year 2–3: internalize critical functions as revenue validates the business model Year 4–5: build full team for EU scale — sales force, country managers, full QA/RA department Shared functions where possible: Quality + Regulatory combined initially; Finance + Admin combined External advisors used for non-recurring expertise: legal, scientific advisory, tax All employment contracts under French labour law (Droit du Travail)

## Organizational Pillars

| Pillar 1 REGULATORY, QUALITY & SCIENCE | Pillar 2 COMMERCIAL & MARKETING | Pillar 3 OPERATIONS & SUPPLY CHAIN | Pillar 4 FINANCE, ADMIN & LEGAL |
| --- | --- | --- | --- |

# 10. DETAILED FUNCTION DESCRIPTIONS & STAFFING PLAN

## 10.1 CEO / General Manager

CEO — Role Summary The CEO holds ultimate P&L responsibility and acts as legal representative (Gérant) of the SARL/SAS. In Year 1, the CEO also carries commercial and business development responsibilities. The CEO is the primary interface with the DIAHO/JCHYTECH partner and chairs the board.

- Define and execute company strategy; manage board relations and investor reporting

- Lead partner relationship with DIAHO/JCHYTECH — contracts, supply, governance

- Drive commercial traction in Year 1 — direct contact with distributors and KOL clinics

- Represent VETALYS at veterinary congresses, trade shows (AFVAC, WSAVA)

Hiring: Founder / Year 1 — compensated via service contract or minimal fixed salary

Required profile: Veterinary diagnostics background OR senior commercial + IVD experience

## 10.2 Pillar 1 — Regulatory Affairs, Quality & Scientific

### RA/QA Manager (ABO)

- Own the regulatory strategy: import compliance, CLP/REACH, French and EU requirements

- Build and maintain technical files for all SKUs — CRITICAL deliverable before any commercial action

- Manage TRACES-NT and CHED-A submissions for animal-derived material imports

- Implement and maintain quality management system: SOPs, batch release, traceability, CAPA

- Lead ISO 9001 certification project (Year 2) and ISO 13485 preparation (Year 3+)

Hiring: Year 1 — part-time consultant or shared resource; Year 2 — full-time CDI hire

Required profile: Bac+5 in life sciences; experience in IVD or veterinary diagnostic RA

### Scientific/Medical Advisor (External+ ABO)

- Provide clinical validation support: study design, data interpretation, literature review

- Advise on allergen panels: clinical relevance for French/EU canine and feline allergy epidemiology

- Support KOL engagement: credibility in veterinary dermatology community

Engagement: External advisor/consultant (advisory fee); no employment contract required

Required profile: Veterinary dermatologist or immunologist; academic or referral clinic affiliation preferred

## 10.3 Pillar 2 — Commercial & Marketing (JCH)

### Chief Commercial Officer / Business Development Manager

- Own the go-to-market execution: distributor negotiations, onboarding, and ongoing relationship management

- Build and manage KOL network: AFVAC congress presence, referral clinic engagement

- Define and execute marketing strategy: positioning, materials, digital presence, congress participation

- Manage sales funnel: awareness → trial → repeat → upsell (reader, array)

- Monitor competitive landscape: pricing moves, new entrants, distributor exclusivity situations

Hiring: Year 1 — JCH carries this role; Year 2 — dedicated CCO hire (CDI)

Required profile: 5+ years veterinary diagnostics or animal health commercial; France market knowledge

### Field Sales Representative(s)

- Direct clinic engagement in target dermatology and allergy-active practices

- Conduct in-clinic product demonstrations and training sessions

- Support distributor sales reps: co-visits, product knowledge, clinical Q&A

- Achieve monthly KPI targets: new clinic activations, demos completed, reorder rates

Hiring: Year 2 (1 rep for France); Year 3 (2nd rep France + 1 international)

## 10.4 Pillar 3 — Operations & Supply Chain (Team France + JCH/ABO)

### Operations Manager / Supply Chain Coordinator

- Manage end-to-end supply chain: JCHYTECH order placement, import customs, 3PL warehousing, distribution

- Maintain inventory levels: safety stock, FEFO management, expiry monitoring

- Coordinate import logistics: liaise with customs broker, SIVEP/BCP for animal-derived shipments

- Manage order management: distributor orders, invoicing, credit terms, dispute resolution

Hiring: Year 1 — CEO/founder handles with external customs broker support; Year 2 — dedicated CDI

## 10.5 Pillar 4 — Finance, Administration & Legal (Team France + JCH/ABO)

### CFO / Finance Manager

- Own financial planning: annual budget, rolling 12-month cash flow forecast, P&L tracking

- Manage cash position: monitor against funding runway, flag requirements early

- Oversee accounting: liaise with external comptable for bookkeeping

- Produce investor reporting: monthly KPI dashboard, quarterly narrative update

- Manage DIAHO loan: repayment tracking, conversion option monitoring, interest accrual

Hiring: Year 1 — founder/CFO role or external comptable

# 11. MASTER MILESTONES TIMELINE

| Period | Key Actions & Milestones |
| --- | --- |
| Q1 2026 (Foundation) | Incorporate VETALYS (SARL/SAS) in Poitiers; register RCS, VAT, EORI Execute all contractual documents with DIAHO (service, supply, option pact) Appoint legal counsel; initiate EUIPO trademark filing for VETALYS brand Engage RA/QA consultant; commission full technical file review Open bank account; set up accounting system |
| Q2 2026 (Compliance) | Complete French labels + IFUs for all SKUs Register UFI/PCN; obtain French SDS for all reagent kits Select and test import route (BCP/SIVEP); test import pilot Implement traceability + vigilance system Initial KOL clinic contacts (5–10 AFVAC-connected dermatology practices) CEO begins distributor conversations (Centravet, Alcyon, Coveto) |
| Q3 2026 (Commercial) | First commercial import batch received + batch released Signed distribution agreement with at least one Tier-1 distributor Demo kits deployed to KOL clinics; clinical feedback collected First invoiced orders to distributor AFVAC congress presence; product presentation Y2 hiring plan finalized: RA/QA CDI + CCO process initiated |
| Q4 2026 (Validation) | 50–100 clinics ordering via distributor Y1 financial performance review vs. model Investor reporting: update on KPIs, cash position, go-forward plan Begin Italy/Spain regulatory preparation (labels, SDS, local regulatory scan) Opportunistic Belgium entry through AFVAC network |
| 2027 (Scale FR) | RA/QA CDI hired; ISO 9001 project launched CCO hired; Field Sales Rep 1 (France) onboarded 2nd distributor agreement signed (France) CE-IVD technical file preparation initiated Italy and Spain first commercial sales via local distributor DX Reader placement program launched with top clinics |
| 2028 (EU Platform) | ISO 13485 certification project active Germany market entry: full regulatory prep, local distribution partner Country Manager for Southern Europe (IT+ES) hired European distribution hub operational or contracted OEM integration in JCHYTECH manufacturing confirmed |
| 2029–2030 (Leadership) | Consolidated EU5 presence with local commercial resources Full QMS ISO 13485 certified Exit readiness: clean IP, regulatory compliance, scalable operations Trade sale preparation OR Series A / strategic investor engagement |

# 12. EXIT STRATEGY

| Preferred Exit Scenarios Trade sale to veterinary diagnostics player (IDEXX, Zoetis, Heska, Nextmune) Strategic acquisition by animal health group (Boehringer, Elanco, Virbac) Partnership/merger with European vet distributor seeking diagnostics vertical | Exit Readiness Requirements Clean IP: EUIPO trademarks, no licensing disputes ISO 13485 certified QMS — standard due diligence requirement Auditable financials (3 years); French GAAP compliant Documented distributor contracts and recurring revenue base |
| --- | --- |

⚠ EXIT WARNING — Veterinary-Only Positioning is Non-Negotiable. The veterinary market has distinct players from human health. Mixing human and veterinary activities or catalogs will disqualify VETALYS from the primary exit pool (animal health acquirers). This is a hard strategic constraint — not a preference.

VETALYS — Precision You Trust, Care They Deserve

Confidential Working Document — April 2026