## Dashboard
Faune Autour Acoustic Sensor — Project Management Dashboard
Metric | Value
Total tasks | 31
Done | 0
In progress | 1
Blocked | 0
Average progress | 1.613%
Critical risks | 1
High risks | 8
Phase | Tasks | Done | Avg progress
0 - Product framing | 3 | 0 | 16.67%
1 - Technical proof of concept | 4 | 0 | 0%
2 - Local connector & schema | 3 | 0 | 0%
3 - Backend API & database | 4 | 0 | 0%
4 - Web dashboard / PWA | 3 | 0 | 0%
5 - Ecological intelligence layer | 3 | 0 | 0%
6 - Outdoor autonomous prototype | 4 | 0 | 0%
7 - Validation & quality control | 2 | 0 | 0%
8 - Multi-station network mode | 2 | 0 | 0%
9 - Productization | 3 | 0 | 0%
How to use this workbook
1 | Edit tasks in Workplan: owner, dates, status and progress.
2 | Use Dependencies to review technical blockers and sequence risks.
3 | Use Competences_RACI to brief/hire the right profiles.
4 | Use Risks weekly; the Score and Level columns are formula-based.
5 | Dashboard updates automatically from Workplan and Risks.
6 | For precise scheduling, replace tentative dates with your actual start date.

## Workplan
ID | Phase | Workstream | Task | Deliverable | Owner role | Start | Duration days | End | Depends on | Status | Priority | Progress % | Dependency OK? | Notes
T001 | 0 - Product framing | Product | Define MVP: fixed Wi-Fi bird station | MVP scope note | Product owner / scientific lead | 46148 | 2 | 46149 |  | In Progress | Critical | 0.5 | No dependency | Birds first; fixed station first
T002 | 0 - Product framing | Scientific | Define target taxa and initial species filters | Target species/filter list | Bioacoustics / zoology | 46149 | 3 | 46151 | T001 | Not Started | High | 0 | Single dependency tracked | Start with local birds
T003 | 0 - Product framing | Product | Define success criteria and field test protocol | Acceptance criteria | Product owner / scientific lead | 46150 | 2 | 46151 | T001 | Not Started | High | 0 | Single dependency tracked | 7-day stability test
T004 | 1 - Technical proof of concept | Hardware | Select Raspberry Pi, microphone, storage kit | Bill of materials v1 | Audio hardware / electronics | 46152 | 2 | 46153 | T001 | Not Started | Critical | 0 | Single dependency tracked | Pi 4/5 + USB mic
T005 | 1 - Technical proof of concept | Edge software | Install OS and configure audio capture | Working audio input | Raspberry Pi / Linux | 46154 | 2 | 46155 | T004 | Not Started | Critical | 0 | Single dependency tracked | Check gain/noise
T006 | 1 - Technical proof of concept | Edge software | Install and configure BirdNET-Go | BirdNET-Go running | Raspberry Pi / Linux | 46156 | 3 | 46158 | T005 | Not Started | Critical | 0 | Single dependency tracked | Use local processing
T007 | 1 - Technical proof of concept | Scientific | Run first 24-hour detection test | First detection log | Bioacoustics / zoology | 46159 | 2 | 46160 | T006 | Not Started | High | 0 | Single dependency tracked | Initial false-positive check
T008 | 2 - Local connector & schema | Data | Define Faune Autour detection JSON schema | Detection schema v1 | Backend/API development | 46157 | 3 | 46159 | T002 | Not Started | Critical | 0 | Single dependency tracked | Scientific name as master key
T009 | 2 - Local connector & schema | Edge software | Create local SQLite queue and log schema | Local queue database | Raspberry Pi / Linux | 46160 | 3 | 46162 | T008 | Not Started | Critical | 0 | Single dependency tracked | Offline-first
T010 | 2 - Local connector & schema | Edge software | Build connector from BirdNET-Go to Faune schema | Connector service v1 | Raspberry Pi / Linux | 46163 | 5 | 46167 | T006,T008,T009 | Not Started | Critical | 0 | Check multi-dependency | Python or Go service
T011 | 3 - Backend API & database | Backend | Design PostgreSQL/PostGIS schema | Server database schema | Database / GIS / PostGIS | 46162 | 4 | 46165 | T008 | Not Started | Critical | 0 | Single dependency tracked | Stations, devices, detections
T012 | 3 - Backend API & database | Backend | Build device authentication and registration | Device registration API | Backend/API development | 46166 | 3 | 46168 | T011 | Not Started | Critical | 0 | Single dependency tracked | Token-based auth
T013 | 3 - Backend API & database | Backend | Build detection ingestion endpoint | POST /detections | Backend/API development | 46169 | 4 | 46172 | T011,T012 | Not Started | Critical | 0 | Check multi-dependency | Accept metadata first
T014 | 3 - Backend API & database | Backend | Build map/query/export endpoints | Map + CSV/GeoJSON API | Backend/API development | 46173 | 4 | 46176 | T013 | Not Started | High | 0 | Single dependency tracked | Support dashboard
T015 | 4 - Web dashboard / PWA | Frontend | Create station map and latest detections view | Dashboard v1 | Frontend / PWA / UX | 46176 | 5 | 46180 | T014 | Not Started | Critical | 0 | Single dependency tracked | MapLibre/Leaflet
T016 | 4 - Web dashboard / PWA | Frontend | Create species timeline and confidence filters | Timeline view | Frontend / PWA / UX | 46181 | 4 | 46184 | T015 | Not Started | High | 0 | Single dependency tracked | Filter by confidence/status
T017 | 4 - Web dashboard / PWA | Frontend | Create station health panel | Device health screen | Frontend / PWA / UX | 46183 | 3 | 46185 | T012,T013 | Not Started | Medium | 0 | Check multi-dependency | Battery/network/storage later
T018 | 5 - Ecological intelligence layer | Integration | Connect BirdWeather API for nearby detections | BirdWeather connector | API integration / data engineering | 46185 | 4 | 46188 | T014 | Not Started | Medium | 0 | Single dependency tracked | Import/public compare
T019 | 5 - Ecological intelligence layer | Integration | Connect occurrence/habitat/weather sources | External enrichment connector | API integration / data engineering | 46189 | 6 | 46194 | T014 | Not Started | High | 0 | Single dependency tracked | GBIF/iNat/OSM/weather
T020 | 5 - Ecological intelligence layer | Scientific | Build expected vs detected logic | Ecological interpretation engine | Bioacoustics / zoology | 46195 | 5 | 46199 | T018,T019,T002 | Not Started | High | 0 | Check multi-dependency | Observed vs expected
T021 | 6 - Outdoor autonomous prototype | Hardware | Design enclosure and microphone protection | Outdoor enclosure v1 | Audio hardware / electronics | 46193 | 5 | 46197 | T004 | Not Started | High | 0 | Single dependency tracked | Condensation and wind/rain
T022 | 6 - Outdoor autonomous prototype | Hardware | Define battery/solar power budget | Energy design note | Audio hardware / electronics | 46198 | 4 | 46201 | T021 | Not Started | High | 0 | Single dependency tracked | Wh/day and margin
T023 | 6 - Outdoor autonomous prototype | Connectivity | Integrate 4G/LTE and offline sync test | Field connectivity test | Raspberry Pi / Linux | 46202 | 5 | 46206 | T010,T013,T022 | Not Started | High | 0 | Check multi-dependency | Retry queue
T024 | 6 - Outdoor autonomous prototype | Field test | Run 7-day outdoor field test | Field test report | Product owner / scientific lead | 46209 | 7 | 46215 | T015,T016,T023 | Not Started | Critical | 0 | Check multi-dependency | Reliability + accuracy
T025 | 7 - Validation & quality control | Scientific | Define validation statuses and thresholds | Validation protocol | Bioacoustics / zoology | 46201 | 4 | 46204 | T007,T020 | Not Started | High | 0 | Check multi-dependency | Unverified/probable/validated/rejected
T026 | 7 - Validation & quality control | Frontend/Backend | Build expert validation screen and audit trail | Validation workflow v1 | Frontend / PWA / UX | 46205 | 6 | 46210 | T025,T015,T013 | Not Started | Medium | 0 | Check multi-dependency | Store review decisions
T027 | 8 - Multi-station network mode | Backend | Add user accounts and station groups | Multi-station backend | Backend/API development | 46211 | 6 | 46216 | T014 | Not Started | Medium | 0 | Single dependency tracked | Public/private stations
T028 | 8 - Multi-station network mode | DevOps | Deploy staging environment with backups and monitoring | Staging platform | DevOps / cloud deployment | 46213 | 5 | 46217 | T013,T014 | Not Started | High | 0 | Check multi-dependency | Docker + HTTPS + backups
T029 | 9 - Productization | Documentation | Write install, maintenance and user guide | Documentation pack | Technical writing / documentation | 46218 | 5 | 46222 | T024,T026 | Not Started | Medium | 0 | Check multi-dependency | Mac-friendly user instructions later
T030 | 9 - Productization | Legal | Draft privacy/GDPR and sensitive species policy | Data governance note | Legal / privacy / GDPR | 46218 | 5 | 46222 | T008,T013,T026 | Not Started | High | 0 | Check multi-dependency | Audio/location/privacy
T031 | 9 - Productization | Product | Finalize v1 product specification and next budget | Product spec v1 | Product owner / scientific lead | 46225 | 4 | 46228 | T024,T028,T029,T030 | Not Started | Critical | 0 | Check multi-dependency | Decision: prototype to pilot

## Dependencies
Task ID | Task | Depends on | Dependency type | Impact if late | Mitigation / comment
T002 | Define target taxa and initial species filters | T001 | Finish-to-start | Delays downstream task | Review dependency weekly
T003 | Define success criteria and field test protocol | T001 | Finish-to-start | Delays downstream task | Review dependency weekly
T004 | Select Raspberry Pi, microphone, storage kit | T001 | Finish-to-start | Delays downstream task | Review dependency weekly
T005 | Install OS and configure audio capture | T004 | Finish-to-start | Delays downstream task | Review dependency weekly
T006 | Install and configure BirdNET-Go | T005 | Finish-to-start | Delays downstream task | Review dependency weekly
T007 | Run first 24-hour detection test | T006 | Finish-to-start | Delays downstream task | Review dependency weekly
T008 | Define Faune Autour detection JSON schema | T002 | Finish-to-start | Delays downstream task | Review dependency weekly
T009 | Create local SQLite queue and log schema | T008 | Finish-to-start | Delays downstream task | Review dependency weekly
T010 | Build connector from BirdNET-Go to Faune schema | T006 | Finish-to-start | Delays downstream task | Review dependency weekly
T010 | Build connector from BirdNET-Go to Faune schema | T008 | Finish-to-start | Delays downstream task | Review dependency weekly
T010 | Build connector from BirdNET-Go to Faune schema | T009 | Finish-to-start | Delays downstream task | Review dependency weekly
T011 | Design PostgreSQL/PostGIS schema | T008 | Finish-to-start | Delays downstream task | Review dependency weekly
T012 | Build device authentication and registration | T011 | Finish-to-start | Delays downstream task | Review dependency weekly
T013 | Build detection ingestion endpoint | T011 | Finish-to-start | Delays downstream task | Review dependency weekly
T013 | Build detection ingestion endpoint | T012 | Finish-to-start | Delays downstream task | Review dependency weekly
T014 | Build map/query/export endpoints | T013 | Finish-to-start | Delays downstream task | Review dependency weekly
T015 | Create station map and latest detections view | T014 | Finish-to-start | Delays downstream task | Review dependency weekly
T016 | Create species timeline and confidence filters | T015 | Finish-to-start | Delays downstream task | Review dependency weekly
T017 | Create station health panel | T012 | Finish-to-start | Delays downstream task | Review dependency weekly
T017 | Create station health panel | T013 | Finish-to-start | Delays downstream task | Review dependency weekly
T018 | Connect BirdWeather API for nearby detections | T014 | Finish-to-start | Delays downstream task | Review dependency weekly
T019 | Connect occurrence/habitat/weather sources | T014 | Finish-to-start | Delays downstream task | Review dependency weekly
T020 | Build expected vs detected logic | T018 | Finish-to-start | Delays downstream task | Review dependency weekly
T020 | Build expected vs detected logic | T019 | Finish-to-start | Delays downstream task | Review dependency weekly
T020 | Build expected vs detected logic | T002 | Finish-to-start | Delays downstream task | Review dependency weekly
T021 | Design enclosure and microphone protection | T004 | Finish-to-start | Delays downstream task | Review dependency weekly
T022 | Define battery/solar power budget | T021 | Finish-to-start | Delays downstream task | Review dependency weekly
T023 | Integrate 4G/LTE and offline sync test | T010 | Finish-to-start | Delays downstream task | Review dependency weekly
T023 | Integrate 4G/LTE and offline sync test | T013 | Finish-to-start | Delays downstream task | Review dependency weekly
T023 | Integrate 4G/LTE and offline sync test | T022 | Finish-to-start | Delays downstream task | Review dependency weekly
T024 | Run 7-day outdoor field test | T015 | Finish-to-start | Delays downstream task | Review dependency weekly
T024 | Run 7-day outdoor field test | T016 | Finish-to-start | Delays downstream task | Review dependency weekly
T024 | Run 7-day outdoor field test | T023 | Finish-to-start | Delays downstream task | Review dependency weekly
T025 | Define validation statuses and thresholds | T007 | Finish-to-start | Delays downstream task | Review dependency weekly
T025 | Define validation statuses and thresholds | T020 | Finish-to-start | Delays downstream task | Review dependency weekly
T026 | Build expert validation screen and audit trail | T025 | Finish-to-start | Delays downstream task | Review dependency weekly
T026 | Build expert validation screen and audit trail | T015 | Finish-to-start | Delays downstream task | Review dependency weekly
T026 | Build expert validation screen and audit trail | T013 | Finish-to-start | Delays downstream task | Review dependency weekly
T027 | Add user accounts and station groups | T014 | Finish-to-start | Delays downstream task | Review dependency weekly
T028 | Deploy staging environment with backups and monitoring | T013 | Finish-to-start | Delays downstream task | Review dependency weekly
T028 | Deploy staging environment with backups and monitoring | T014 | Finish-to-start | Delays downstream task | Review dependency weekly
T029 | Write install, maintenance and user guide | T024 | Finish-to-start | Delays downstream task | Review dependency weekly
T029 | Write install, maintenance and user guide | T026 | Finish-to-start | Delays downstream task | Review dependency weekly
T030 | Draft privacy/GDPR and sensitive species policy | T008 | Finish-to-start | Delays downstream task | Review dependency weekly
T030 | Draft privacy/GDPR and sensitive species policy | T013 | Finish-to-start | Delays downstream task | Review dependency weekly
T030 | Draft privacy/GDPR and sensitive species policy | T026 | Finish-to-start | Delays downstream task | Review dependency weekly
T031 | Finalize v1 product specification and next budget | T024 | Finish-to-start | Delays downstream task | Review dependency weekly
T031 | Finalize v1 product specification and next budget | T028 | Finish-to-start | Delays downstream task | Review dependency weekly
T031 | Finalize v1 product specification and next budget | T029 | Finish-to-start | Delays downstream task | Review dependency weekly
T031 | Finalize v1 product specification and next budget | T030 | Finish-to-start | Delays downstream task | Review dependency weekly

## Competences_RACI
Competence / Role | Main responsibility | Phase involvement | R | A | C | I | Notes
Product owner / scientific lead | Product scope, priorities, field validation | All phases | Yes | Yes | Yes |  | Could be JC
Bioacoustics / zoology | Species filters, thresholds, validation, ecology | 0,1,5,7 | Yes | Yes | Yes |  | Protects scientific credibility
Raspberry Pi / Linux | Device OS, BirdNET-Go, local queue, services | 1,2,6 | Yes |  | Yes |  | Critical prototype role
Audio hardware / electronics | Microphone, enclosure, power, solar/battery | 1,6 | Yes |  | Yes |  | Critical for outdoor version
Backend/API development | Server API, authentication, ingestion, station data | 2,3,8 | Yes | Yes | Yes |  | Core platform
Database / GIS / PostGIS | Geospatial schema, queries, exports | 3,5,8 | Yes |  | Yes |  | Map and biodiversity queries
Frontend / PWA / UX | Dashboard, map, validation interface | 4,7,8 | Yes |  | Yes |  | User-facing clarity
API integration / data engineering | BirdWeather, GBIF, weather, OSM integrations | 5 | Yes |  | Yes |  | Phase 2 enrichment
DevOps / cloud deployment | Docker, staging, backups, monitoring, HTTPS | 3,8,9 | Yes |  | Yes |  | Needed before pilot
Legal / privacy / GDPR | Audio, location, consent, sensitive species rules | 7,9 | Yes | Yes | Yes |  | Before public launch
Technical writing / documentation | Install and maintenance docs | 9 | Yes |  | Yes |  | Productization

## Risks
Risk ID | Category | Risk | Probability 1-5 | Impact 1-5 | Score | Level | Mitigation | Owner role | Status
R001 | Scientific | False positives create unreliable species list | 4 | 5 | 20 | Critical | Use confidence thresholds, geographic/seasonal filters, expert validation | Bioacoustics / zoology | Open
R002 | Technical | Raspberry Pi unstable during continuous inference | 3 | 4 | 12 | High | Watchdog, logs, thermal monitoring, staged tests | Raspberry Pi / Linux | Open
R003 | Hardware | Microphone quality insufficient outdoors | 3 | 5 | 15 | High | Field microphone tests, wind/rain protection, gain calibration | Audio hardware / electronics | Open
R004 | Connectivity | Outdoor station loses network connection | 4 | 3 | 12 | High | Offline queue, retry logic, 4G antenna, local storage | Raspberry Pi / Linux | Open
R005 | Energy | Solar/battery autonomy underestimated | 3 | 5 | 15 | High | Measure real Wh/day, oversized battery, scheduling | Audio hardware / electronics | Open
R006 | Privacy | Device records human voices or sensitive location data | 3 | 5 | 15 | High | Local processing, no raw audio upload by default, GDPR policy | Legal / privacy / GDPR | Open
R007 | Data | Taxonomy mismatch between sources | 3 | 4 | 12 | High | Use scientific name and taxon IDs as master keys | Database / GIS / PostGIS | Open
R008 | Product | Scope creep: birds, bats, insects too early | 4 | 4 | 16 | High | Birds-only MVP; add taxa in later phases | Product owner / scientific lead | Open
R009 | API | External API limits or terms block integration | 2 | 4 | 8 | Medium | Cache data, respect terms, avoid single-provider dependency | API integration / data engineering | Open
R010 | Deployment | No backups/monitoring before pilot | 3 | 4 | 12 | High | Deploy staging with automated backup and monitoring | DevOps / cloud deployment | Open

## Lists
Status | Priority | Phase | Competence | RACI | Risk Level
Not Started | Critical | 0 - Product framing | Product owner / scientific lead | Responsible | Low
In Progress | High | 1 - Technical proof of concept | Bioacoustics / zoology | Accountable | Medium
Blocked | Medium | 2 - Local connector & schema | Raspberry Pi / Linux | Consulted | High
Done | Low | 3 - Backend API & database | Audio hardware / electronics | Informed | Critical
Deferred |  | 4 - Web dashboard / PWA | Backend/API development
|  | 5 - Ecological intelligence layer | Database / GIS / PostGIS
|  | 6 - Outdoor autonomous prototype | Frontend / PWA / UX
|  | 7 - Validation & quality control | API integration / data engineering
|  | 8 - Multi-station network mode | DevOps / cloud deployment
|  | 9 - Productization | Legal / privacy / GDPR
Technical writing / documentation